## Sheet1
Division | Performance Standard What do you want to achieve? | Performance Measures How will you measure progress? | Data Sources Where will performance data come from? | Frequency How often will the data be collected and analyzed? | Baseline Janaury 2018 Where are we as of January? | Target December 2018 Where do we want to be? | Responsible Person/ Party Who will monitor and report performance? | Cumulative Percent completed 9/30/18 | Cumulative Percent Completed 12/31/2018
Emergency Preparedness |  | 2 Community Preparedness Programs Presented | Flyers | Bi-annually | 0% | 100% | Nurse | 0% | Removed from SOW
| All Immediately Reportable infectious disease reports will be investigated within 24 hours | % of Immediately Reportable disease reports investigated within 1 day | Communicable Disease Reporting & Surveillance System | Quarterly |  | 100% | PH Nurse | 3/3 100% | 4/4 100%
Nursing
|  | % of Reportable disease reports investigated within 72 hours (excluding tick-borne disease and chronic hep B/C, investigated within 7 days) | CDRSS "Cases updated by User" report | Quarterly |  | 100% | PH Nurse | 27/29 93% | 12/12 100%
|  | # of schools and daycare centers audited | Immunization Audit Report | Monthly |  | 100% | PH Nurse | 2019 task | All 2019 audits scheduled
Nursing | Schools and daycare centers will be audited annually as per NJAC 8:57 Standards | % of deficient facilities followed up within 30 days | Immunization Audit Report | Monthly |  | 100% | PH Nurse | 2019 task
| 100% of outbreaks will be documented in CDRSS within 24 hours of detection of outbreak. | % of outbreaks reported to NJDH within timeframes | CDRSS | Quarterly |  | 100% | PH Nurse | 0/0 | 0/0
Nursing
| Monthly Reports provided to Branchburg Health Officer by 10th of the month | % of reports submitted within that timeframe | Monthly Report | Monthly |  | 100% | PH nurse | 0/3 | 1/3 33%
Health Education | Complete health education monthly reports before the 10th of the month | % of reports submitted within that timeframe | Monthly Report | Monthly |  | 100% | Health Educator | 0/3 | 1/3 33%
Health Education | Implementation of CDSMP series | # of evidence-based health promotion programs completed | 1 program | Annually | 50% | 100% | Health Educator | removed
|  | Develop & Implement marketing strategy 90 days before program | 1 marketing strategy implemented | 3X/year | 33% | 100% |  | 3 physicians contacted for communicable Disease education
# of attendees completeing series
| Attending Back to School Nights for relationship-building and marketing | [5 empty] | Health Educator; PHN; Staff
|  | # of BTS Nights attended | # of Schools | September/October | 80% | 100% | Health Educator | 3 of 3 100%